## wc 09.02.26
Street Address | Town | Start Date | End Date | Start time | End time | TM Type | Promoter | Works | Works location description | Works location | Comment | Community Board
CHINNOR ROAD | BLEDLOW RIDGE | 2026-02-11 | 2026-02-11 | 8:00 | 18:00 | Multi-way signals | UK POWER NETWORKS EASTERN & LONDON | Network Operations Distribution: Install / Replace / Remove overhead lines and poles: Bus Stop Suspension: Installing backfeed | Junction with Chinnor Road and Haw Lane Chinnor Road, HP14 4AP | Verge |  | West Chilterns
HIGHFIELD ROAD | BOURNE END | 2026-02-14 | 2026-02-22 |  |  | Multi-way signals | CADENT GAS LIMITED | GAS MAINS REPLACEMENT â€“ IMGA2521602 ABANDON 100M X 2" SI MAIN AND 63MM PE OPEN CUT AND RELAY OR TRANSFER SERVICES FOR WORKS CARRIED O UT BY CADENT GAS | FROM O/S NO 32-34 TO WESTFIELD SCHOOL | Footway, Carriageway |  | West Chilterns
MARLOW ROAD | BOURNE END | 2026-02-02 | 2026-02-02 | 9:30 | 15:30 | Two-way signals | BT | 2-WAY TRAFFIC LIGHTS AND FOOTPATH CLOSURE REQUIRED TO ENABLE DP22 TO BE RENEWED. | Marlow Road Wooburn Little Marlow Buckinghamshire England SL8 5PH. Work on verge. | Verge | AMENDMENT. Report 05/02/26 amends dates from 02/02/26 to 20/02/26 | West Chilterns
MARLOW ROAD | BOURNE END | 2026-02-14 | 2026-02-15 |  |  | Multi-way signals | BT | LAY APPROX 60M OF NEW BT DUCT. APPROX 300MM WIDTH 480MM DEPTH | FROM O/S BOURNE COTTAGE TO O/S WESSEX HOUSE | Footway |  | West Chilterns
THE PARADE | BOURNE END | 2026-02-14 | 2026-02-15 |  |  | Multi-way signals | BT | LAY APPROX 20M OF NEW BT DUCT. APPROX 300MM WIDTH 480MM DEPTH. WORKS OUTSIDE SECTION 58 | FROM OPP 73 TO OPP 67 | Footway |  | West Chilterns
BRADENHAM ROAD | BRADENHAM | 2026-02-10 | 2026-02-11 | 0:00 | 23:59 | Two-way signals | Buckinghamshire Council | Lift and reset gully and repair materials around ironwork as per the method statement. Bedding frame with Envirobed mortar and surrounding the frame with PY4/5 resin mortar leaving 40mm depth for 10mm hot tarmac2 way lightsRLee ¦1734479 (DR - Damaged Gully) | on left going towards wycombe | Carriageway |  | West Chilterns
MISSENDEN ROAD | BUTLERS CROSS | 2026-02-09 | 2026-02-14 |  |  | Road closure | Buckinghamshire Council | Maintenance of trees adjacent to carriageway | works over the carriageway and verge | Carriageway, Verge |  | West Chilterns
CHAPEL ROAD | FLACKWELL HEATH | 2026-02-14 | 2026-02-15 |  |  | Multi-way signals | THAMES WATER | FIRE HYDRANT INSTALL IN FWAY/VERGE | 15 CHAPEL ROAD, FLACKWELL HEATH, HP10 9AA | Footway, Verge |  | West Chilterns
GROVE LANE | GREAT KIMBLE | 2026-02-05 | 2026-02-09 | 9:00 |  | Two-way signals | THAMES WATER | SERVICE PIPE REPAIR IN FWAY/VERGE | O/S GROVE FARM, GROVE LANE, GREAT KIMBLE, HP17 9TR | Footway, Verge |  | West Chilterns
GROVE LANE | GREAT KIMBLE | 2026-02-09 | 2026-02-09 |  |  | Road closure | Buckinghamshire Council | SIGN INSTALLATION ON BRIDGE | WORKS TAKING PLACE ON BRIDGE | Carriageway, Verge |  | West Chilterns
COCKPIT ROAD | GREAT KINGSHILL | 2026-02-05 | 2026-02-10 |  |  | Two-way signals | GIGACLEAR LIMITED | Remedial works to rectify HAD only , kerb replacement | Outside Adelaide | Footway, Carriageway |  | West Chilterns
STAG LANE | GREAT KINGSHILL | 2026-02-06 | 2026-02-10 |  |  | Multi-way signals | GIGACLEAR LIMITED | Remedial to rectify HAD in carriageway | ADJ hedgerows | Footway, Carriageway |  | West Chilterns
HEATHFIELD ROAD | HEDSOR | 2026-02-09 | 2026-02-12 |  |  | Two-way signals | Buckinghamshire Council | Tree maintenance works. | Next to sign | Carriageway |  | West Chilterns
VALLEY ROAD | HUGHENDEN VALLEY | 2026-02-09 | 2026-02-13 | 9:30 | 15:30 | Two-way signals | SCOTTISH AND SOUTHERN POWER DISTRIBUTION (SSEPD) | NEED TO PLACE TRAFFIC CONTROL WHILE OPERATIVES WORK ON THE OVERHEAD LINES | O/S Hitchenden Farm Cottages to o/s Entrance to Magnolia Park | Footway, Carriageway |  | West Chilterns
FORTY GREEN ROAD | KNOTTY GREEN | 2026-02-02 | 2026-02-06 |  |  | Road closure | CADENT GAS LIMITED | PHASE 2-GAS MAINS REPLACEMENT â€“ IMGA262131 ABANDON 56M X 6" SI MAIN AND INSERT 125MM PE AND RELAY OR TRANSFER SERVICES FOR WORKS CA RRIED OUT BY CADENT GAS | FROM THE J/O BRINDLE LANE TO O/S LOOS COTTAGE | Footway, Carriageway | AMENDMENT. Report 05/02/26 amends dates to 09/03/26 - 13/03/26.
WITHERIDGE LANE | KNOTTY GREEN | 2026-02-11 | 2026-02-12 | 0:00 | 23:59 | Two-way signals | Buckinghamshire Council | Lift and reset gully and renew materials around ironwork as per the method of measurement. Bedding frame with Envirobed mortar and surrounding the frame with PY4/5 resin mortar leaving 40mm depth for 10mm hot tarmac2 way lightsRLee ¦1723465 (DR - Damaged Gully) | on lft when westbound | Carriageway |  | West Chilterns
MARLOW ROAD | LANE END | 2026-02-09 | 2026-02-10 |  |  | Multi-way signals | Buckinghamshire Council | Multiple carriageway defect repairs. | by Clayton Road | Carriageway | Report 05/02/26 shows revised dates from 15/01/26 - 16/01/26 to 09/02/26 - 10/02/26 | West Chilterns
STATION ROAD | LITTLE KIMBLE | 2026-02-11 | 2026-02-13 |  |  | Two-way signals | Buckinghamshire Council | INSTALL TMP GROUND SOCKET AND TMP EVO-NR PLUS KEEP LEFT BOLLARD ONLY. DISCONNECT DNO SUPPLY AND SWA SUPPLY CABLE. REMOVE DAMAGED MINI FEEDER PILLAR TO TIP. INSTALL NEW MINI FEEDER PILLAR. TRANSFER DNO SUPPLY. TRANSFER SWA SUPPLY CABLE. FIT CHEN/L2 ISOLATOR. 1X 6A MD FUSE. 1M 10MM EARTH CABLE. | NEAR TO STATION HOUSE Next to Island station side | Carriageway |  | West Chilterns
BERWICK ROAD | MARLOW | 2026-02-03 | 2026-02-09 | 7:00 | 19:00 | Road closure | Buckinghamshire Council | Micro Surfacing Prep works | Selected USRN | Carriageway |  | West Chilterns
DEAN STREET | MARLOW | 2026-02-09 | 2026-02-10 | 0:00 | 23:59 | Multi-way signals | Buckinghamshire Council | Full Carriageway RepairPlease excavate to 0.1m depthReinstate with adequate layers including 10mm surface layerDimensions: 2.5x1.6Suggested TM: 3 way lightsRenew give way linesRL ¦1744069 (CW - Pothole) | on queens road junction | Carriageway |  | West Chilterns
HIGH STREET | MARLOW | 2026-02-14 | 2026-02-15 |  |  | Road closure | Buckinghamshire Council | RELEASING LOAD FOR BEARING REPLACEMENT | MARLOW BRIDGE | Carriageway |  | West Chilterns
THE CAUSEWAY | MARLOW | 2025-06-07 | 2026-06-01 | 7:00 | 16:00 | Road closure | TRANSITION TOWN MARLOW | MARKET - 1st and 3rd Saturday of every month
WEST STREET | MARLOW | 2026-02-14 | 2026-02-15 |  |  | Multi-way signals | THAMES WATER | Boundary Box Exchange FWAY - customer job | 'O/S10,10,WEST STREET, SL7 2NB | Footway |  | West Chilterns
WILTSHIRE ROAD | MARLOW | 2026-01-05 | 2026-02-12 |  |  | Multi-way signals | CADENT GAS LIMITED | IMGA262118 GAS MAINS REPLACEMENT - ABANDON 575MTRS X 6 SI MAIN AND INSERT 125MM PE AND RELAY OR TRANSFER SERVICES FOR WORKS C ARRIED OUT BY CADENT GAS | OUTSIDE REAROF NO 7 JAMES CLOSE TO THE ROUNDABOUT ON LITTLE MARLOW ROAD | Footway, Carriageway |  | West Chilterns
MAIN ROAD | NAPHILL | 2025-10-06 | 2026-02-20 | 8:00 | 17:00 | Multi-way signals | AFFINITY WATER - C | MAINS RENEWALS | FROM COOMBES LANES UNTIL CLAPPINS LANE | Footway, Carriageway |  | West Chilterns
CHURCH STREET | PRINCES RISBOROUGH | 2026-02-10 | 2026-02-12 |  |  | Two-way signals | THAMES WATER | CHAMBER AND COVER REPAIR IN CWAY | CORNER COTTAGE, CHURCH STREET, PRINCES RISBOROUGH, HP27 9AA | Carriageway |  | West Chilterns
HORSENDEN LANE | PRINCES RISBOROUGH | 2026-02-12 | 2026-02-12 |  |  | Road closure | Buckinghamshire Council | Tree maintenance works. | As plotted | Carriageway |  | West Chilterns
PICTS LANE | PRINCES RISBOROUGH | 2026-02-04 | 2026-02-10 | 9:25 | 23:00 | Two-way signals | UK POWER NETWORKS EASTERN & LONDON | Network Operations Faults: Essential and immediate repair to Low Voltage single service cable affecting customers supply. Additional work may be required to safeguard supplies: EXCAVATION FOR A SERVICE FAULT | OPP 52. HP27 9DX. | Verge |  | West Chilterns
BENNETT END ROAD | RADNAGE | 2026-02-03 | 2026-04-28 |  |  | Road closure | THAMES WATER | Full mains replacement - including service relays and connections | Bowers Lane to Horseshoe Road | Footway, Carriageway, Verge |  | West Chilterns
HORSESHOE ROAD | RADNAGE | 2026-01-06 | 2026-03-09 |  |  | Road closure | THAMES WATER | Full mains replacement including service relays and connections | Town End Road to Bennett End Road | Footway, Carriageway, Verge |  | West Chilterns
WYCOMBE ROAD | SAUNDERTON | 2026-02-03 | 2026-02-09 | 19:00 | 7:00 | Road closure | Buckinghamshire Council | Surface dressing prep | Selected USRN | Carriageway | Night works | West Chilterns
WYCOMBE ROAD | SAUNDERTON | 2026-02-06 | 2026-02-06 | 9:30 | 15:30 | Multi-way signals | Buckinghamshire Council | Tree maintenance works. | As Plotted | Carriageway | AMENDMENT. Report 05/02/26 amends dates from 06/02/26 to 19/03/26
WYCOMBE ROAD | SAUNDERTON | 2026-02-10 | 2026-02-10 | 8:00 | 17:00 | Two-way signals | THAMES WATER | Install new air valve in chamber | Opp Sunrise HP27 | Verge |  | West Chilterns
WYCOMBE ROAD | STUDLEY GREEN | 2026-01-12 | 2026-03-04 | 7:00 | 17:00 | Multi-way signals | SCOTTISH AND SOUTHERN POWER DISTRIBUTION (SSEPD) | Excavation of approx 1100m for Installation of new 33kV cable and associated fibre optic in CW as part of network reinforcement. | 280m from ent to ivanhoe house to j/o dashwood hill | Carriageway |  | West Chilterns
BRADENHAM ROAD | WEST WYCOMBE | 2026-02-13 | 2026-02-14 | 20:00 | 6:00 | Road closure | Buckinghamshire Council | Remedial structure repair works | As plotted in area of railway bridge | Carriageway |  | West Chilterns
WYCOMBE LANE | WOOBURN GREEN | 2026-02-14 | 2026-02-22 |  |  | Two-way signals | CADENT GAS LIMITED | (3INCH) Permit for trial holes to determine the condition and material of main as per HSE mandated works | Wycombe Lane outside 160 | Footway |  | West Chilterns
WATERY LANE | WOOBURN MOOR | 2026-02-11 | 2026-02-11 | 9:30 | 15:30 | Multi-way signals | THAMES WATER | sewer clean | rolling 4 way lights | Carriageway |  | West Chilterns
Marlow Suspension Bridge (Monday 3rd November to March 2026) During November, all works will take place underneath the bridge, with minimal impact on traffic (NO road closures or lane closures). The only visible changes will be some suspended parking bays near the park and Pound Lane car park.
Note: Dates correct at time of publishing but could be subject to change. Excludes immediate works.
ADVANCE NOTICE: UK Highways M40 Ltd manages and maintains the M40 on behalf of National Highways. As part of their ongoing monitoring of the M40, it has come to their attention that necessary repair works will be required to the 50- year-old viaduct at Loudwater High Wycombe. In summary, works are expected to include concrete repairs, maintenance painting of steelwork, bearing refurbishment and replacement. The Loudwater Viaduct works are currently being planned to be undertaken from Spring 2026 to Winter 2026, and will require the closure of the junction 3 slip road, specific dates will be confirmed nearer the time. Diversion routes etc are not yet available as the works are still out to tender.